BNC Preventive Maintenance Shutdown

May 2 – May 7, 2010

Six-Week Notice

The BNC will be shut down during the week of May 2 for preventive and corrective maintenance activities.  This shutdown will be more extensive than previous shutdowns – major electrical work will take place that will shut down electrical power to the building during the early morning hours of May 3.  It is expected that this work will be complete prior to 8:00 AM on Monday, May 3.

Please note that the cleanroom and the building exhaust systems will be down for the entire week.  No chemicals or hazardous gases may be used during this period.

Tentative Shutdown Schedule – Updates will be sent closer to the shutdown period

10:00 PM 	Sunday, May 2	Laboratories and cleanroom will be shut down at Sunday evening at 10:00 pm.  No chemicals or hazardous materials may be used.  Electrical power to the building will be shut down in the early morning hours of May 3, including all office power.

12:00 Midnight 	Monday, May 3	The building will be closed to all people except those involved in the shutdown activities.  Offices will be without electrical power, as will most building systems.  Please shut down computers and critical systems prior to this time.

8:00 AM 	Monday, May 3	We expect to have building power restored.  The building and offices will be open, but laboratories and cleanroom will still be closed.  There may be instabilities in temperature during this time.

12:00 Noon 	Monday, May 3	Building systems stabile.  Temperature should be normal at this time.

8:00 AM 	Wednesday, May 5	The laboratories will be opened to the use of nonhazardous materials.  No chemical processing (acid or solvent) or hazardous gases may be used.

3:00 PM 	Friday, May 7	Cleanroom and Laboratories fully functional.  Hazardous materials may be used.

IMPORTANT NOTE:  This schedule lists building systems.  For the status of processing or characterization equipment, please see Coral.  Some equipment may be shut down prior to the shutdown and some may remain down subsequent to the shutdown.