## Revised Schedule 3Dec12
Shutdown Summary |  | Updated 10 December 2012
Who | Reason | Affected | Begins | Duration | Operational
Purdue | Reduce Exhaust | Entire East Wing | 2012-11-12 | 1 day | 2012-11-12 | 17:00
Wilhelm | Remove Fan | Entire East Wing | 2012-11-14 | 4 hrs | 2012-11-14 | Noon
Wilhelm | Set MAU | Area under crane | 11/30/2012* | 1 day | 2012-11-30 | 17:00
Wilhelm | Set new fans | Area under crane | 12/17/2012** | 1 day | 2012-12-17 | 17:00
Wilhelm | Move operating fan | Entire East Wing | 2012-12-17 | 5 days | 2012-12-21 | 17:00
Wilhelm | Start-up new exhaust and MAU | Entire East Wing
Purdue | Balance airflow | Entire East Wing
Wilhelm | Rework Lab Ductwork | BRK 2087 | 2012-12-03 | 5 wks | 2013-01-07 | 17:00
Purdue | Balance airflow | BRK 2087
Wilhelm | Rework Lab Ductwork | BRK 2043 | 2013-01-15 | 5 wks | 2013-02-15 | 17:00
Purdue | Balance airflow | BRK 2043
Wilhelm | Rework Lab Ductwork | BRK 1081 | 2013-02-04 | 3 wks | 2013-02-22 | 17:00
Purdue | Balance airflow | BRK 1081
Wilhelm | Rework Lab Ductwork | BRK 2077 | 2013-02-18 | 3 wks | 2013-03-08 | 17:00
Purdue | Balance airflow | BRK 2077
*Delayed from previously scheduled time |  |  | **New Shutdown
COMPLETE

## Original Schedule with Updates
Shutdown Summary |  | Updated 3 December 2012
Who | Reason | Affected | Begins | Duration | Operational |  | Notes
Purdue | Reduce Exhaust | Entire East Wing | 2012-11-12 | 1 day | 2012-11-12 | 17:00 | Self-managed, completed within timeframe
Wilhelm | Remove Fan | Entire East Wing | 2012-11-14 | 4 hrs | 2012-11-14 | Noon | Completed within timeframe; major mistake during demolition caught by Mark Voorhis
Wilhelm | Set MAU | Area under crane | 2012-11-21 | 1 day | 2012-11-21 | 17:00 | FAILED. Requires TWO shutdowns now, first scheduled for 11/30/12
Wilhelm | Move operating fan | Entire East Wing | 2012-11-26 | 3 days | 2012-11-26 | 17:00 | Completed within timeframe.
Wilhelm | Start-up new exhaust and MAU | Entire East Wing | 2012-12-03 | 5 days | 2012-12-07 | 17:00 | Postponed
Purdue | Balance airflow | Entire East Wing
Wilhelm | Rework Lab Ductwork | BRK 2087 | 2012-12-03 | 5 wks | 2013-01-07 | 17:00 | Delayed - awaiting more info from Wilhelm
Purdue | Balance airflow | BRK 2087
Wilhelm | Rework Lab Ductwork | BRK 2043 | 2013-01-07 | 5 wks | 2013-02-08 | 17:00
Purdue | Balance airflow | BRK 2043
Wilhelm | Rework Lab Ductwork | BRK 1081 | 2013-01-28 | 3 wks | 2013-02-15 | 17:00
Purdue | Balance airflow | BRK 1081
Wilhelm | Rework Lab Ductwork | BRK 2077 | 2013-02-11 | 3 wks | 2013-03-01 | 17:00
Purdue | Balance airflow | BRK 2077