## Slide 1: Nano-Bio Wing Exhaust Project
Update 3 October 2012
J. R. Weaver  3 October 2012

## Slide 2: Discussion
Scope of Project
  Penthouse
  Laboratories
Project Timing
  Penthouse Work
  Laboratory Work
Action Items
  Hood Priority List
Summary of Events

## Slide 3: Project Scope
Penthouse
  Install new makeup-air system
  Move two existing exhaust fans
  Install two new exhaust fans
Laboratories
  Rework ductwork to accommodate increased airflow

## Slide 4: Project Timing
Penthouse Work
  Begins November, 2012
Laboratory Work
  Begins December, 2012
  Order of Laboratories
    Lab 2087
    Lab 2043
    Lab 1081
    Lab 2077
  Estimated completion March, 2013

## Slide 5: Penthouse Work
Shut down hoods to allow one-fan operation
  Approximately 30% reduction in exhaust needed
  Shutdown and rebalance early November
  Return to normal operation by mid December
Rebalance exhaust and makeup air systems to ensure proper airflow
  One hood at a time
  All hoods in East Wing (both floors)

## Slide 6: Penthouse Work (CONTINUED)
Install new makeup-air unit
  Shutdown areas under crane while lifting in place
    Preliminary schedule: November 21, 2012
Move existing exhaust fan
Install new exhaust fans
  Rebalance hoods for four-fan operation
  Begin operations with all four fans by mid December

## Slide 7: Tentative Shutdown Schedule
Penthouse Work
 | Projected Date | Projected Duration
Reduce exhaust | 11/12/2012 | 1 day
Remove fan | 11/14/2012 | 4 hrs
Set makeup air unit | 11/21/2012 | 1 day
Move operating fan | 11/26/2012 | 3 days
Start-up new exhaust and MAU | 12/3/2012 | 5 days
During these shutdown periods there will be no exhaust available to the hoods and biosafety cabinets in the east wing of the BNC, but the laboratories may be occupied. No solvents or biological materials requiring exhaust may be used.
Certain labs may not be occupied during this time, others may operate as normal.

## Slide 8: Laboratory Work – Laboratory owner
Prior to beginning of construction
  Remove all sensitive equipment from laboratory
  Clear all work surfaces and shelving units
After laboratory released
  Reinstall laboratory equipment
  Restart research!

## Slide 9: Laboratory Work – Contractor
Protect equipment left in laboratory
  e.g., optical tables, hoods
Demo existing ductwork and booster fans
Rework ductwork
Install filters on return air where applicable
Reinstall ceiling
Balance exhaust and incoming air

## Slide 10: Laboratory Work – Tentative Schedule
BRK 2087
  Move equipment out of lab prior to December 2, 2012
  Begin construction in lab December 3, 2012
  Release lab for move-in December 21, 2012
  Begin operations in lab January 7, 2013

## Slide 11: Laboratory Work – Tentative Schedule
BRK 2043
  Move equipment out of lab prior to January 6, 2013
  Begin construction in lab January 7, 2013
  Release lab for move-in January 25, 2013
  Begin operations in lab February 8, 2013

## Slide 12: Laboratory Work – Tentative Schedule
BRK 1081
  Move equipment out of lab prior to February 3, 2013
  Begin construction in lab January 28, 2013
  Release lab for move-in February 8, 2013
  Begin operations in lab February 15, 2013

## Slide 13: Laboratory Work – Tentative Schedule
BRK 2077
  Move equipment out of lab prior to February 10, 2013
  Begin construction in lab February 11, 2013
  Release lab for move-in March 1, 2013
  Begin operations in lab March 15, 2013

## Slide 14: Summary
Penthouse work requires 4 shutdowns
  During November and December, 2012
  Ranging from 4 hrs. to 5 days in length
  No exhaust is available during shutdown
    NOTE: One shutdown does not allow laboratory occupancy, others restrict chemical and biological usage
Laboratory work shuts down one laboratory at a time.

## Slide 15: Summary
Work is tentatively scheduled to begin on November 12, 2012
Completion is scheduled for March 15, 2013
Immediate action item is to set the priority list for hood closures
Updates will be sent out as they are available

## Slide 16: Summary of Shutdown Events
Tentative Schedule as of 2 October 2012
Shutdown Summary |  | Updated 3 October 2012 |  |  |  | 
Who | Reason | Affected | Begins | Duration | Operational | 
Purdue | Reduce Exhaust | Entire East Wing | 11/12/2012 | 1 day | 11/12/2012 | 5:00 PM
Wilhelm | Remove Fan | Entire East Wing | 11/14/2012 | 4 hrs | 11/14/2012 | Noon
Wilhelm | Set MAU | Area under crane | 11/21/2012 | 1 day | 11/21/2012 | 5:00 PM
Wilhelm | Move operating fan | Entire East Wing | 11/26/2012 | 3 days | 11/26/2012 | 5:00 PM
Wilhelm | Start-up new exhaust and MAU | Entire East Wing | 12/3/2012 | 5 days | 12/7/2012 | 5:00 PM
Purdue | Balance airflow | Entire East Wing |  |  |  | 
Wilhelm | Rework Lab Ductwork | BRK 2087 | 12/3/2012 | 5 wks | 1/7/2013 | 5:00 PM
Purdue | Balance airflow | BRK 2087 |  |  |  | 
Wilhelm | Rework Lab Ductwork | BRK 2043 | 1/7/2013 | 5 wks | 2/8/2013 | 5:00 PM
Purdue | Balance airflow | BRK 2043 |  |  |  | 
Wilhelm | Rework Lab Ductwork | BRK 1081 | 1/28/2013 | 3 wks | 2/15/2013 | 5:00 PM
Purdue | Balance airflow | BRK 1081 |  |  |  | 
Wilhelm | Rework Lab Ductwork | BRK 2077 | 2/11/2013 | 3 wks | 3/1/2013 | 5:00 PM
Purdue | Balance airflow | BRK 2077 |  |  |  | 

## Slide 17: Working together we can pull this off!