## Sheet1
Shutdown Summary |  | Updated 3 October 2012
Who | Reason | Affected | Begins | Duration | Operational
Purdue | Reduce Exhaust | Entire East Wing | 2012-11-12 | 1 day | 2012-11-12 | 17:00
Wilhelm | Remove Fan | Entire East Wing | 2012-11-14 | 4 hrs | 2012-11-14 | Noon
Wilhelm | Set MAU | Area under crane | 2012-11-21 | 1 day | 2012-11-21 | 17:00
Wilhelm | Move operating fan | Entire East Wing | 2012-11-26 | 3 days | 2012-11-26 | 17:00
Wilhelm | Start-up new exhaust and MAU | Entire East Wing | 2012-12-03 | 5 days | 2012-12-07 | 17:00
Purdue | Balance airflow | Entire East Wing
Wilhelm | Rework Lab Ductwork | BRK 2087 | 2012-12-03 | 5 wks | 2013-01-07 | 17:00
Purdue | Balance airflow | BRK 2087
Wilhelm | Rework Lab Ductwork | BRK 2043 | 2013-01-07 | 5 wks | 2013-02-08 | 17:00
Purdue | Balance airflow | BRK 2043
Wilhelm | Rework Lab Ductwork | BRK 1081 | 2013-01-28 | 3 wks | 2013-02-15 | 17:00
Purdue | Balance airflow | BRK 1081
Wilhelm | Rework Lab Ductwork | BRK 2077 | 2013-02-11 | 3 wks | 2013-03-01 | 17:00
Purdue | Balance airflow | BRK 2077