## Slide 1: Birck Nanotechnology Center Modernization Project Sequences
Mark Voorhis, Birck Facilities Manager
Ron Reger, Birck Engineering Manager
Mark Sammons, Project Manager – Purdue University Capital Assets Management
Rhett Eckert, Project Manager - Pepper Construction Inc.

## Slide 2: Birck Nanotechnology Center Modernization Project
Timeline for Project – Sequences of Bay & Chase Work

## Slide 3: Birck Nanotechnology Center Modernization Project
Green
Bays remain open for research
New equipment installations and minor construction work
Blue
Bays/chases closed for major construction
No research work while construction is underway
Some mitigation plans for specific bays
Goals
Reduce downtime in bays/chases
Manage disruptions as much as possible
Relocate research work when possible
Plan installations to facilitate tool availability
Communicate progress frequently
Sequence 1
P-Bay and PP Chase “Clean Construction” 4/1/2024 - 4/26/2024
Current JEOL stays available for research
Installation of vibration base and new JEOL in south half of the bay.
NO anneal furnace relocate to Q-Bay
N2 anneal furnace removed
Metrology tools relocated & stay available in M-Bay
Sequence 2
JK Chase “Clean Construction” 4/1/2024 - 4/26/2024
Install two new PlasmaTherm Etchers, Silicon & Oxide
PlasmaTherm start-up and commissioning
Allows later removal of old STS AOE & ASE in L-Bay
Panasonic, PlasmaTherm, & e-Beams available
Sequence 3
P-Bay & PQR Chase “Clean Construction” 4/29/2024 - 5/3/2024
Install relocated NO anneal furnace
AJA Ion Mill available for research use
Sequence 5:
G Bay & GH Chase Closed: 25 Business Days, 7/15/2024 - 8/16/2024
Bay closed to cleanroom aisle
Major construction
No access to ALDs in the Bay or Chase
Sequence 4
J-Bay & JK Chase Closed: 48 Business Days, 5/6/2024 - 7/12/2024
Bay closed to cleanroom aisle
Characterization tools have been moved to 2037, 2043
Major construction
No access to the AJA PVD system
No access to Kurt Lesker PVD system
Sequence 6
L Bay & LM Chase Closed: 48 Business Days, 8/19/2024 - 10/11/2024
Bay closed to cleanroom aisle
Major construction
Silicon and oxide etchers in new PlasmaTherms in K-Bay
Removal of old STS ASE & AOE
No access to GLAD, AJA, new PVD, or CHA2 evaporators
Sequence 7
RS Chase “Clean Construction” 10/14/2024 - 12/6/2024
Installation of new fume hoods
Thermal work (R-Bay) and sputtering work (S-Bay) continues
Sequence 9
D Bay & DE Chase, E Bay & EE Chase Closed: 50 Business Days 2/17/2025 - 4/25/2025
Major construction, wall removal
Removal of Maxwell Roll to Roll system
Removal of Mirwec system
Opens up large bay for future use
Sequence 8
D Bay & AD Chase “Clean Construction” 12/9/2024 - 2/14/2025
Install new fume hoods, planning for photoresist work temporary relocation
Sequence 10
F Bay Clean Construction 2/17/2025 - 3/5/2025
Remove and relocate dilution refrigerator
Nanoscribe and other soft material work continues
Sequence 11
M Bay & MN - LM Chases Closed: 44 Business Days 4/28/2025 - 6/27/2025
Bay closed to cleanroom aisle
Fume hoods removed & replaced with new hoods
Metrology tools relocated a second time to remain available
New fume hoods available for photo processing in D-Bay and RS chase
Sequence 12
N Bay & MN Chase Closed: 36 Business Days 6/30/2025 - 8/19/2025
Bay closed to cleanroom aisle
Fume hoods removed & replaced with new hoods
Photoresist spinners available in other hoods
Microscopes temporarily relocated and available
Apreo SEM, Heidelberg, and contact aligners unavailable